“Spatial Information Management for Sustainable Real Estate Market

Best Practice Guidelines on Nation-wide land administration”

Athens, 28-31 May 2003

Modernising cadastral records in Romania

F Ciobanu, M Calineanu, I Savoiu and D W Harris

April 2003

AUTHORS

Florin Ciobanu – Vice-President, National Office for Cadastre, Geodesy and Cartography (ONCGC) – is a professional surveyor with wide experience in academia, and public and private sector surveying organisations.

Mihail Calineanu - Director of the Cadastre Implementation Group, ONCGC – is an experienced senior official of the Romanian Cadastre with overall responsibility for the modernization programme of the Cadastre.

Ionut Savoiu – General Manager BlomInfo Romania and Deputy Project Manager of Cadastral services based on orthophotos project (CSBOP) Dambovita County – is a professional surveyor and founder-manager of a successful and growing Romanian private surveying company.

David Harris – Project Manager, CSBOP – is an independent professional surveyor from the UK, with extensive recent experience of cadastre and land registration in the countries of central and Eastern Europe.

ABSTRACT

Romania has made much progress in transferring ownership of real estate from the state to the private sector, following the demise of the communist Government in 1989.  The Government is now implementing a programme of modernising real estate records in the Cadastre and Land Books to support the development of a land market. A World Bank loan is funding the conversion of maps and documents to digital form.  The results will simplify the quality improvement of the information, enable a more efficient means of maintaining the records and support more effective distribution of information to users.

- Introduction.  Before the communists came to power, agricultural land in Romania was highly fragmented.  Subsequent nationalisation (1947-62) of the land to form state and co-operative farms produced large and inefficient units.

- Post 1989 land reforms.  Following the fall of communism in 1989, the new Government made the restitution of private land rights a priority.  The process has been continuing ever since; currently over 90% of the land has been restituted.  However, this has returned the agricultural holdings to a fragmented pattern, with holdings now averaging  1-3 ha.  In urban areas most residential property is now privately owned, though the privatisation of commercial premises has proceeded more slowly.  In addition there has been much progress in introducing legislation to support the private ownership of land, though significant work still needs to be done.

- Achieving objectives – strategy.  The history of successive land reforms has combined with rapid change over the past 14 years to produce a complex situation.  Restitution has varied in speed in different parts of the country.  The quality of the work has been uneven due to the pressure to work quickly and the lack of skilled surveyors and lawyers to map new boundaries and document changes.  The increasing demand to register property rights has also led to variation in the quality of ‘sporadic’ boundary surveys.  The de facto changes on the ground are not always accurately reflected in de jure records in the cadastre and land book.

The main strategy for dealing with these issues is to produce a cadastral index map which positions and uniquely identifies each property.  This is achieved by converting all available records (maps and documents) to digital form, referenced to an orthophoto base map.  This enables gaps, errors and conflicts within the data to be assessed and resolved, while enabling the growing real estate market to be supported at the same time.

- Achieving objectives – procedures.  The county of Dambovita, north-west of Bucharest, was chosen as one of the first counties to be ‘converted’ using the above approach.  Dambovita county is a pilot in the “General Cadastre and Land Registration Project”, financed by the International Bank for Reconstruction and Development – World Bank.  A contract was let to a private Romanian-Norwegian joint venture company which commenced work in February 2002.  The basic process has been:

- Collect and record all available legal maps and documents held by the local cadastre office

- Collect de facto ownership and boundary information in the field, using graphical survey methods and local knowledge

- Scan all the documents and maps from the above processes

- Geo-reference and vectorise property boundary and other relevant information (e.g. selected buildings) on the orthophoto base, allocating a unique index number to each property

- Enter the ownership information into a relational database

- Combine the resulting digital textual and graphical information to form an index map and database of properties and owners

- Benefits of the approach.  The main benefits of this approach are:

- Enables the best use to be made of all existing data, thus minimising ‘re-work’

- All information is placed on a uniform and consistent graphical base

- Significant positional errors and conflicts can easily be seen

- Information from a wide range of documentary sources is brought together in one system

- Conflicting or dubious ownership information (e.g. duplicate owners) is highlighted and recorded for future resolution

- Errors are catalogued and can be solved on a sporadic or systematic basis as required

- Gaps in the property record are easily seen

- Results can easily be output for display in communities, enabling de facto records to be converted to de jure through appropriate procedures

- Changes required because of the operation of the land market (sale, mortgage, sub-division) can be done more efficiently, and always related to relevant existing information

- Links to other public databases - e.g. the Land Books - are easier

- Future plans.  The above procedures form the beginning of the development of a modern cadastral system in Romania.  The main tasks for the future are:

- Maintaining the initial dataset

- Prioritise other areas of Romania for extension of the methodology

- Test an alternative approach which does not use an orthophoto base

- Develop a pricing strategy for recouping costs

- Develop strategies for improving data quality

Develop methods and strategies for data supply to users

# Introduction

## Country background

Romania covers an area of 237,500 sq km of which:

- 15,000 sq km are settlements and infrastructure

- 148,000 sq km are agricultural land

- 67,000 sq km are forests

Romania’s population is estimated at 22.5 million.  About 51% of the population live in urban areas, more than 2 million in the capital of Bucharest.  The country is bordered by the Yugoslavian Federation of Serbia & Montenegro, and Hungary to the west; Bulgaria to the south; the Black Sea, Ukraine and Moldavia to the east and north.  The southern and south-eastern parts of the country and the area bordering on Hungary are made up of flat fertile plains while the centre and northern areas, dominated by the Carpathian Mountains, are hilly to mountainous.

## Land Reform prior to 1989

Agricultural land had been transformed from a highly fragmented pattern of ownership in pre-communist times, to an over-centralised system with production units much too large to be efficient, followed by fragmented ownership again after the revolution.  In 1941, an average farm holding was about 4.5 ha, divided into about four to five plots.  Collectivisation began in 1948 but progressed slowly at first with 10% of arable land expropriated by 1956.  It accelerated rapidly to 77% in 1962.  By 1989, 10.9 million hectares of agricultural land were under state farms and cooperatives.  Only 1.8 million hectares remained in private ownership in about one million remote and fragmented mountain farms.

When the land was expropriated for collectivisation, inventories were made listing the names of the former owners, the approximate area and quality of land and a description of the location.  No maps were drawn.  Many of these lists still exist but some were destroyed and larger landowners tended to under-declare their holdings for different reasons.  More accurate information was available in Transylvania (see map) where the Land Book (Grundbuch) system was introduced in 1865.  Its cadastral maps and land books have generally survived, describing land and property, titles and other land rights although they were not maintained for a long period of time.  However, informal transactions on land and property (sales and inheritance) have always continued.

# Recent history of the cadastral system in Romania

## Land Reform since 1989

One of the early and most radical reforms of the government that came to power after the 1989 revolution was the restitution of private rights to land and real estate.  Agricultural land reform has focussed on redistributing the land in cooperative farms and issuing share certificates in the state farms to former land owners and farm workers.  Although the land reform program has progressed well, its influence on private sector development has been limited.  Private sector agriculture has largely been limited to subsistence farming because of the fragmentation of land into small holdings, averaging about 1-3 ha and in many cases less.  In urban areas, private property is increasing as apartments are purchased from the state, state enterprises are being privatised and new businesses are emerging.  The privatisation of state enterprises has been considerably delayed, but the process has accelerated in the last few years.

## Legislative development

Significant progress has been made in bringing about fundamental changes in the land laws.  The legal basis for land restitution is Land Fund Law no. 18 of 1991 which re-establishes the rights of Romanian citizens and companies to own and exchange land and other property.  Law 18/1991 was amended and extended by

- Land Lease Law no. 16 of 1994, amended and extended by Law no. 65 of 1998

- Law no. 7 of 1996 on General Cadastre and real estate publicity (for details see below)

- Law no 169 of 1997 and Law 1 of 2000 stipulating land ownership reconstitution for agricultural and forest land

- Land Circulation Law no. 54 of 1998

- Law no. 268 of 2001 stipulating the privatisation of the commercial companies which administer the private and public state owned agricultural land and setting up the State Domain Agency

Before 1996 when Law no. 7 on General Cadastre and Real Estate Publicity was enacted, two systems of land registration existed in Romania:

- Civil Code inscription and transcription system

- Land Book (Grundbuch) system in the areas of Transylvania, Banat and Bucovina (see map on page 4).

The Civil Code system had been operated in 24 Judets , the Land Book system in 14 Judets; three Judets have had a mixture of both systems.  Both the systems suffered and fell under disuse before 1989 as most of the land was collectivised and no records of parcels and ownership were maintained.

Law 7/1996.  This law defines the cadastre and land book system and its elements as the unique system for systematic or sporadic registration of land and property by shape, location and size.  It also defines the state institutions in charge of maintaining the system and their responsibilities, methods and tools, and provides for the extension of the Land Book system to the whole country and the establishment of a new organizational framework.  Due to the low resources available for systematic cadastre projects for mass registration in the Land Book, a sporadic registration system was set up for transacted land properties.  Land reform activities were not registered and the old land book system still survives where there is no new system. The first systematic approach is Dambovita County where further development is expected.  The National Office for Cadastre Geodesy and Cartography (ONCGC) under the Ministry of Public Administration is now responsible for the new cadastral system in Romania.  ONCGC – assimilated as the National Mapping Agency - has 42 local offices (OJCGC): one office in each Judet and one in Bucharest.

This sound legislative foundation now needs to be complemented by registering titles, land ownership rights and transactions.

## ONCGC

Initially the “National Office for Cadastre Geodesy and Cartography“ (ONCGC) was not involved in land reform activities.  These were carried out by local Agricultural Cadastre Offices under the supervision of the Ministry of Agriculture, which was in charge of land restitution until 2001.  However, since 2001 (by amending Law no. 7) these local Ministry of Agriculture offices have been incorporated into the OJCGC structure in the Ministry of Public Administration.

During the past ONCGC included strategy, regulation, administration and representation roles in its field of activity.  In order to fulfil the above mentioned roles ONCGC now performs the following activities:

- Leads, organises, controls and supervises cadastre, geodetic, topographic, remote sensing, photogrammetry and mapping works

- Initiates regulation, laws and technical specifications

- Ensures the identification, measurement, evaluation and registration of the parcels and their identifiers in the cadastral documents

- Transfers the owners’ registration to the land registry (Land Book)

- Manages the data management system of owners and land parcels in paper and IT environments

- Coordinates land reform activities

- Certifies private surveyors and surveying companies

- Integrates all cadastre data

- Regulates agricultural and forest land-use change

- Maintains the state geodetic control point network

- Coordinates and controls systematic and sporadic cadastral registrations

- Together with the Ministry of Justice organises information exchange with Land Book offices

# Current development of the Romanian cadastral system

## Funding

International funding and development agencies have increasingly recognised the link between land markets, the market economy and democracy and make funds available for national agencies active in the cadastre and land registration sector.

In 1998 a loan was signed between the Government of Romania and the World Bank designated to a “General Cadastre and Land Registration Project”.  Two agencies are involved in this project – ONCGC is responsible for the Cadastre and the Ministry of Justice is responsible for Land Registration (in the Land Books).

The project addresses issues related to:

- Providing security for private property ownership rights

- Establishing a simple institutional set up for safe and cost effective land transactions

- Allowing open access to real estate ownership information that would encourage a transparent land market.

This project started in 1999 and at present the implementation is on going.

## Objectives

The cadastre component supports the following main elements:

- Works (USD 0.1 million)

- Goods (USD 2.0 million)

- Technical services (USD 13.8 million)

  - Service contracts for aerial photography and orthophoto mapping

  - Cadastre services based on (new) orthophoto maps or existing maps

  - Procurement and installation of a cadastre information system

- Consultant Services and Training (USD 1 million)

- Institutional strengthening (USD 0.5 million)

The overall objectives of the Cadastre - Land Book system are:

- Create a general cadastre system which provides a clear and current definition of real estate

- Secure land ownership rights

- Simple and cost-effective land transactions

- Help create a dynamic land market

- A Register of real property rights in a nationwide Land Book system

- Provide comprehensive and current mapping in rural and urban areas

- Support land consolidation

- Foster the development of a private sector capable of surveying, mapping and data collection

# Achieving objectives - strategy

## General approach

The long-term history of successive land reforms has combined with rapid change over the past 14 years to produce a complex situation.  Restitution has varied in speed in different parts of the country.  The quality of the work has been uneven due to the pressure to work quickly and the lack of skilled surveyors, lawyers and administrators to map new boundaries and document ownership changes.  The increasing demand to register property rights (for sale or mortgage) has led to variation in the quality of ‘sporadic’ boundary surveys.  The de facto changes on the ground are not always accurately reflected in de jure records in the cadastre and land book, due to informal transactions (e.g. on inheritance).  Finally a uniform system has never existed in all parts of the country.  Thus complications exist both on the ground and in the documentation which is intended to accurately reflect the ground situation.

One of the main elements of the strategy for dealing with these issues is to produce a cadastral index map which positions and uniquely identifies each property.  This is linked - via the unique identifiers created for each property - to a database of textual information concerning owners and their ownership rights.

This is achieved by converting all available records (maps and documents) to digital form, referenced to an up-to-date orthophoto map base.  Rapid data conversion is achieved so that at a later time, gaps, errors and conflicts within the data can be assessed and resolved, while enabling the growing real estate market to be supported at the same time.

## Advantages of this approach

The overall approach is to provide cost-efficient solutions based on existing cadastral data.  The specific advantages of this method are:

- Enables best use to be made of existing data, so that the amount of ‘re-work’ is minimised

- Information from a wide range of existing documentary sources is brought together into one system

- Enables problems and inconsistencies to be assessed, so that strategies can be developed for resolving them.  These might include sporadic or systematic methods

- Enables new or revised data to be incorporated directly into the new system

- The cadastral index plan approach does not require really high accuracy cadastral surveys

- Provides a sound and uniform basis for future developments and changes

- The use of an orthophoto base means that:

- a variety of survey methods can be used, e.g. graphical, total stations, GPS

- new surveys can be conducted sporadically or systematically

- existing surveys can be fitted to the same base, and inconsistencies easily highlighted

- The potential to link with other public databases, e.g. the land book

# Achieving objectives - procedures

The information below is based on work undertaken in one of the first areas in Romania to be ‘converted’ using the above approach: Dambovita County, north-west of Bucharest.  The work was begun in February 2002 (using orthophoto maps made previously) by a joint venture Norwegian-Romanian company, BlomInfo Romania, based in the city of Targoviste, the administrative capital of Dambovita.

The 41 counties of Romania are divided into ‘administrative territories’, known as communa.  These are the smallest Romanian administrative units and were the basic unit of planning during the conversion production process.  Dambovita comprises 80 administrative territories, of which 73 were included in the data conversion contract.

## Data conversion

The data conversion procedures are shown in diagrammatic form on page 11.  The basic production steps are as follows:

- Orthophoto mapping is produced of the target area, based on the national co-ordinate system

- An inventory is made of all relevant maps and documents

| DOCUMENT TYPE | TEXT | GRAPHIC | Scale | Unique ID | Period |
| --- | --- | --- | --- | --- | --- |
| Cadastre documentation for sporadic registration | Yes | Yes | 1:500-1:2000 | Yes | 1999-2002 |
| Parcelling projects for Land reform Laws | No | Yes | 1:2000 | Yes | 1991-2002 |
| Land reform ownership titles | Yes | No | No | Yes | 1991 – 2002 |
| Land book forms | Yes | No | No | Yes | 1999 – 2002 |
| Cadastre documents for certification of land ownership for former state companies | Yes | Yes | 1:500-1:2000 | No | 1992 |
| Field identification works based on orthophoto in intravillan areas; | Yes | Yes | 1:2000 | Yes | 2002 |
| General urban planning map of the administrative territory; | No | Yes | 1:5000 | No | 1996 -2002 |
| General cadastre map of the administrative territory; | No | Yes | 1:1000 | No | 1984 – 2002 |
| Special cadastre documentation(urban, roads, railroads, electricity lines); | Yes | Yes | 1:500 | Yes | 1994 |

- All existing documents of real estate ownership (including the field collected data) are scanned

- All existing maps of real estate (including the classically surveyed boundaries) are scanned and geo-referenced

- The geo-referenced property boundaries are vectorised

- Graphical and textual printouts are made of the above information

- The printouts are used by field survey teams to define the position of remaining intravilan property boundaries, and to collect ‘de facto’ ownership information

- The field collected information is scanned and combined with the existing information (graphic and textual)

- Each property is given a unique index number to form a simplified graphical base, the Cadastral Index Plan.

- Textual data is entered into a relational database (using on-screen images of the scanned documents)

- The graphical and textual data for each property are integrated, so that each can be used to search the other

The size of the task can be seen from the statistical table on page 12, which summarises the main numbers of document types, owners and properties.

## Problems with existing records

During the conversion process, many inconsistencies were discovered in the existing records.  The basic principle was to gather all the existing data together so that any problems, inconsistencies or ‘gaps’ in the record were highlighted – then they can be assessed and a strategy for resolving them developed.  However, the information in the documentation had to be put into a consistent structure as defined by the client (ONCGC); so some of the inconsistencies could not be ignored; at least partial resolution was needed at the processing stage.

## De jure - de facto

Differences between the ‘de jure’ situation (according to legal documents) and the ‘de facto’ situation (on the ground) exist.  These may be due to informal transactions.  These situations are highlighted in the database, although in general the policy was always to give priority to the legal documents.

## Source document errors

Errors in the source documentation were quite common, e.g. conflicting information in different legal documents.  These were often due to different procedures being used in the land reform process (which was originally done by the Ministry of Agriculture), or to a lack of quality control during the land reform process.  Not all of these problems could be resolved quickly, but many were resolved through liaison between the contractor and local authorities and/or the local (county) office of the OJCGC.

## Geographical differences

There are geographical differences in the land records between areas of Romania, due to the different history of parts of the country.  For example, the Land Book system was only operative in 14 (fully) and 3 (partly) of the 41 Romanian counties.

There are differences in the speed and quality with which the 1990s land reform was done (varying form communa to communa).  There are also variations in the extent to which agricultural land was co-operativised during the period 1948-1989.  This latter situation was a factor in Dambovita, and resulted in changes being made to the processing workflow between ‘co-operativised’ and ‘un co-operativised’ areas.

## Accuracy

Survey errors are highlighted by the orthophoto mapping: one advantage of using orthophotos.  Due to the pressure for accelerated land reform in the early 1990s, there are variations in the quality of ‘parcelation plans’ (surveys of the sub-division of the co-operativised farms into small parcels).  The approach in conversion was to provide a ‘best fit’ of the plans to the orthophotos.  Some of the survey work will have to be re-done in the future, when resources are available.

## Physical condition

There are variations in the physical condition of many paper records.  This is due to their age and the conditions under which they have been kept.  Also, during communist times, many of the records had become redundant, so the incentive for keeping them in good condition was not great.  Document quality affected the speed of processing documents for scanning and data entry.

## Property location

Individual (‘sporadic’) property registration has taken place over the past 5 years.  This requires a ‘sporadic registration survey’, i.e. a survey of the individual property and its boundaries.  Many of these surveys were made on local co-ordinate systems without a suitable location plan.  This made the surveys difficult to locate on the orthophotography based on the national co-ordinate system.  These problems were solved by close co-operation between the contractor and the local Cadastre office (OJCGC).

# Learning lessons

The benefit of hindsight enables us to give some useful guidance to those considering a similar approach to improving the land records in their country.

## Client contractor relationship

This work is an excellent example of public-private sector co-operation.  A good working relationship between client and contractor is essential to success.  This requires a positive attitude on both sides so that problems can be solved, and a willingness to spend significant amounts of time discussing issues and alternative approaches to solving specific problems.

Success in this was achieved by regular focussed meetings between client and contractor senior management teams to resolve specific technical and procedural problems.  One of the project senior management team was designated prime client liaison officer, which ensured he was aware of all relevant issues from both client and contractor perspectives.  Both client and contractor were prepared to meet at short notice.

## Specification development

It is certain that the legal contract (between client and contractor) will not make clear all issues, particularly during earlier contracts.  The final specification will need to be developed during the early stages of the production process, as real problems are encountered.  This will only be possible if there is a good working relationship between client and contractor.

## Planning

The process is complex and requires effective co-ordination and planning.  Experience has shown that the plans need to be constantly revised due to changes in production procedures, for example where significant numbers of errors are discovered in the source data.

## Metadata

There is a very complex relationship between property records compiled in different eras, using diverse methods, by different agencies for varying purposes under changing political and administrative regimes.  Accuracy varies considerably; data relating to the same item (e.g. owners name) may not be identical in different records; ID numbers which should be unique may be duplicated.  Informal changes and transactions further complicate the situation.

Resolving these issues will take time and resources, beyond the immediate scope of converting the records to digital form.  Therefore it is important to record within the digital data ‘metadata’.  This data - about the data itself - such as the source of the information (e.g. document type), accuracy of the survey and survey method is essential to ensure that in the future informed decisions are made about resolving errors and inconsistencies in the data.

# Future plans and options

## Priorities

The work achieved so far is just the beginning of a major and expensive operation to modernise the Romanian Cadastre and Land Registration system.  Inevitably decisions will have to be made – based on priorities – about what work to do next.  The estimates show that Romania has a total of about 8.000.000 properties divided amongst its 22.5 million people.  But the potential for growth of the land market will vary greatly between different areas.  This is the first difficult decision: where should effort in the immediate future be focussed?  Additionally, there are important decisions to be made concerning:

## Data maintenance

The data being processed is becoming out of date even while it is being processed.  The initial data must be maintained in the local offices of the Cadastre and Land Books.  In fact the software to achieve this is already being developed.  The work needs to be expedited to ensure full benefit of the initial conversion work is achieved.

## Data ‘Exposure’

As explained above, a significant amount of the processed data is ‘de facto’ information, based on field collection without reference to any legal documents.  This will have limited value unless its status is changed to ‘de jure’, i.e. being legally valid.  The data should be ‘exposed’, i.e. put on public display in the communa, so that owners and claimants can produce legally valid documentation to support their ownership claims.

## Conversion expansion

Dambovita is just one of 42 counties in Romania.  Similar work has been going on in Prahova, the county to the east of Dambovita.  There is clearly a need to expand the work into other areas.  There are current plans to try alternative approaches to data conversion, including one based on existing maps rather than new orthophotos.

## Data supply

The success of the conversion programme will be in proportion to the level of use of the data.  This goes well beyond the immediate needs of the Cadastre and Land Book offices.  Web based product supply is one clear way forward and can enable users to access up to date data quickly and cheaply, while maintaining the integrity and security of the database.

## Revenue

Maximising revenue will be necessary to support future funding of the expansion and maintenance of the data.  However, to achieve this a balance is needed between price and incentive to use, particularly in the early years – as too high prices will turn potential users away.

## Conclusions

The Romanian Government has made an important step in making the modernising of the Cadastre and Land Registration system a high priority.  In order to achieve the maximum return on the money invested they will need to ensure that clear decisions on priorities are made and close management of the public and private sector organisations involved in the work.

# Footnotes

Judet = county